## $50M table Q1 2014-15
Table 1.10 Capital Expenditure Projects Greater Than $50 million 1
Note: Information in bold type denotes changes from Budget 2014 released on February 18, 2014.
[5 empty] | Project |  | Estimated | Anticipated |  |  | Project Financing
|  |  |  | Year of | Cost to |  | Cost to | Total | Internal/ | P3 |  | Federal | Other
| ($ millions) |  |  | Completion | Jun 30, 2014 |  | Complete | Cost | Borrowing | Liability |  | Gov't | Contrib'ns
Taxpayer-supported
School districts
| Southern Okanagan Secondary 2……………………………………………………………………………………………….. |  |  | 2013 | 50 |  | 4 | 54 | 52 | 0 |  | 0 | 2
| Chilliwack Secondary 2……………………………………………………………………………………………….. |  |  | 2013 | 53 |  | 5 | 58 | 58 | 0 |  | 0 | 0
| Centennial Secondary ……………………………………………………………………………………………….. |  |  | 2015 | 9 |  | 52 | 61 | 61 | 0 |  | 0 | 0
| Oak Bay Secondary ……………………………………………………………………………………………….. |  |  | 2015 | 18 |  | 34 | 52 | 50 | 0 |  | 0 | 2
| Kitsilano Secondary ……………………………………………………………………………………………….. |  |  | 2015 | 8 |  | 56 | 64 | 60 | 0 |  | 0 | 4
| Belmont Secondary ……………………………………………………………………………………………….. |  |  | 2015 | 18 |  | 38 | 56 | 30 | 0 |  | 0 | 26
| Seismic mitigation program ……………………………………………………………………………………………….. |  |  | 2023 | 20 |  | 1280 | 1300 | 1300 | 0 |  | 0 | 0
|  | Total school districts ……………………………………………………………………………………………………….. |  |  | 176 |  | 1469 | 1645 | 1611 | 0 |  | 0 | 34
Post secondary institutions
Emily Carr University of Art and Design
– Campus redevelopment at Great
|  | Northern Way ……………………………………………………………………………………………….. |  | 2017 | 4 |  | 130 | 134 | 113 | 0 |  | 0 | 21
|  | Total post secondary institutions ……………………………………………………………………………………………………….. |  |  | 4 |  | 130 | 134 | 113 | 0 |  | 0 | 21
Health facilities
Northern Cancer Control Strategy 2
| – Direct procurement ……………………………………………………………………………………………………………………….. |  |  | 2014 | 27 |  | 8 | 35 | 32 | 0 |  | 0 | 3
| – P3 contract …………………………………………………………………………………………………………………………………………….. |  |  | 2012 | 71 |  | 0 | 71 | 54 | 17 |  | 0 | 0
Lions Gate Hospital (Mental Health)
| Redevelopment ………………………………………………………………………………………………………… |  |  | 2014 | 41 |  | 21 | 62 | 38 | 0 |  | 0 | 24
| Lakes District Hospital ………………………………………………………………………………………………………… |  |  | 2015 | 24 |  | 31 | 55 | 46 | 0 |  | 0 | 9
| Queen Charlotte/Haida Gwaii Hospital ………………………………………………………………………………………………………… |  |  | 2015 | 9 |  | 41 | 50 | 31 | 0 |  | 0 | 19
Surrey Emergency/Critical Care Tower
| – Direct procurement ……………………………………………………………………………………………………………………….. |  |  | 2016 | 114 |  | 80 | 194 | 174 | 0 |  | 0 | 20
| – P3 contract …………………………………………………………………………………………………………………………………………….. |  |  | 2014 | 318 |  | 0 | 318 | 139 | 179 |  | 0 | 0
| Royal Inland Hospital ………………………………………………………………………………………………………… |  |  | 2016 | 2 |  | 78 | 80 | 47 | 0 |  | 0 | 33
| North Island Hospitals ………………………………………………………………………………………………………… |  |  | 2017 | 15 |  | 591 | 606 | 365 | 0 |  | 0 | 241
Interior Heart and Surgical Centre
| – Direct procurement ……………………………………………………………………………………………………………………….. |  |  | 2017 | 106 |  | 147 | 253 | 213 | 0 |  | 0 | 40
| – P3 contract …………………………………………………………………………………………………………………………………………….. |  |  | 2015 | 92 |  | 36 | 128 | 4 | 79 |  | 0 | 45
Vancouver General Hospital – Joseph and
|  | Rosalie Segal Family Health Centre ………………………………………………………………………………………………………… |  | 2017 | 3 |  | 79 | 82 | 57 | 0 |  | 0 | 25
Children's and Women's Hospital …………………………………………………………………………………………………………
| – Direct procurement ……………………………………………………………………………………………………………………….. |  |  | 2019 | 68 |  | 241 | 309 | 177 | 0 |  | 0 | 132
| – P3 contract …………………………………………………………………………………………………………………………………………….. |  |  | 2017 | 39 |  | 330 | 369 | 168 | 187 |  | 0 | 14
| Clinical and systems transformation ………………………………………………………………………………………………………… |  |  | 2023 | 45 |  | 435 | 480 | 480 | 0 |  | 0 | 0
|  | Total health facilities ……………………………………………………………………………………………………….. |  |  | 974 |  | 2118 | 3092 | 2025 | 462 |  | 0 | 605
Transportation
South Fraser Perimeter Road
| – Direct procurement ……………………………………………………………………………………………………………………….. |  |  | 2014 | 1069 |  | 7 | 1076 | 728 | 0 |  | 348 | 0
| – P3 contract …………………………………………………………………………………………………………………………………….. |  |  | 2014 | 188 |  | 0 | 188 | 0 | 188 |  | 0 | 0
| Sierra Yoyo Desan Road upgrade ……………………………………………………………………………………………………………………………… |  |  | 2014 | 134 |  | 3 | 137 | 137 | 0 |  | 0 | 0
Evergreen Line Rapid Transit
| – Direct procurement ……………………………………………………………………………………………………………………….. |  |  | 2016 | 241 |  | 301 | 542 | 327 | 0 |  | 74 | 141
| – P3 contract …………………………………………………………………………………………………………………………………….. |  |  | 2016 | 413 |  | 476 | 889 | 0 | 259 |  | 350 | 280
|  | Total transportation ………………………………………………………………………………………………………… |  |  | 2045 |  | 787 | 2832 | 1192 | 447 |  | 772 | 421
Table 1.10 Capital Expenditure Projects Greater Than $50 million 1 (continued)
Note: Information in bold type denotes changes from Budget 2014 released on February 18, 2014.
[5 empty] | Project |  | Estimated | Anticipated |  |  | Project Financing
|  |  |  | Year of | Cost to |  | Cost to | Total | Internal/ | P3 |  | Federal | Other
| ($ millions) |  |  | Completion | Jun 30, 2014 |  | Complete | Cost | Borrowing | Liability |  | Gov't | Contrib'ns
Other taxpayer-supported
| Integrated Case Management system………………………………………………………………………………. |  |  | 2014 | 165 |  | 17 | 182 | 179 | 0 |  | 3 | 0
Single Room Occupancy Hotel renewal initiative
| – Direct procurement ……………………………………………………………………………………………………………………….. |  |  | 2016 | 10 |  | 15 | 25 | 23 | 0 |  | 2 | 0
| – P3 contract …………………………………………………………………………………………………………………………………….. |  |  | 2016 | 55 |  | 63 | 118 | 0 | 91 |  | 27 | 0
Okanagan Correctional Centre
| – Direct procurement ……………………………………………………………………………………………………………………….. |  |  | 2016 | 13 |  | 74 | 87 | 87 | 0 |  | 0 | 0
| – P3 contract …………………………………………………………………………………………………………………………………….. |  |  | 2016 | 11 |  | 118 | 129 | 8 | 121 |  | 0 | 0
|  | Total other ……………………………………………………………………………………………………………………………………….. |  |  | 254 |  | 287 | 541 | 297 | 212 |  | 32 | 0
|  |  | Total taxpayer-supported ............................................................................ |  | 3453 |  | 4791 | 8244 | 5238 | 1121 |  | 804 | 1081
Self-supported
Transportation
| Port Mann Bridge / Highway 1 ........................................................................................ |  |  | 2015 | 3232 |  | 87 | 3319 | 3319 | 0 |  | 0 | 0
Power generation and transmission
BC Hydro
| – Seymour Arm series capacitor 2………………………………………………………………………… |  |  | 2014 | 47 |  | 2 | 49 | 49 | 0 |  | 0 | 0
| – Vancouver City Central transmission 2………………………………………………………………………… |  |  | 2014 | 170 |  | 1 | 171 | 171 | 0 |  | 0 | 0
| – Mica gas insulated switchgear replacement ………………………………………………………………………… |  |  | 2014 | 165 |  | 34 | 199 | 199 | 0 |  | 0 | 0
| – Northwest transmission line ………………………………………………………………………… |  |  | 2014 | 645 |  | 101 | 746 | 359 | 0 |  | 130 | 257
| – Merritt area transmission ………………………………………………………………………… |  |  | 2014 | 25 |  | 40 | 65 | 65 | 0 |  | 0 | 0
| – Smart metering and infrastructure program ………………………………………………………………………………………. |  |  | 2015 | 694 |  | 236 | 930 | 930 | 0 |  | 0 | 0
| – Dawson Creek/Chetwynd area transmission ………………………………………………………………………… |  |  | 2015 | 99 |  | 197 | 296 | 296 | 0 |  | 0 | 0
| – Interior to Lower Mainland transmission line ………………………………………………………………………… |  |  | 2015 | 458 |  | 267 | 725 | 725 | 0 |  | 0 | 0
| – GM Shrum units 1 to 5 turbine upgrade ………………………………………………………………………… |  |  | 2015 | 126 |  | 146 | 272 | 272 | 0 |  | 0 | 0
| – Iskut extension project ………………………………………………………………………… |  |  | 2015 | 31 |  | 149 | 180 | 140 | 0 |  | 0 | 40
| – Surrey area substation project ………………………………………………………………………… |  |  | 2015 | 22 |  | 72 | 94 | 94 | 0 |  | 0 | 0
– Hugh Keenleyside spillway gate reliability
| upgrade ………………………………………………………………………… |  |  | 2015 | 77 |  | 46 | 123 | 123 | 0 |  | 0 | 0
| – Mica units 5 and 6 project ………………………………………………………………………… |  |  | 2015 | 439 |  | 275 | 714 | 714 | 0 |  | 0 | 0
| – Long Beach reinforcement ………………………………………………………………………… |  |  | 2015 | 9 |  | 47 | 56 | 56 | 0 |  | 0 | 0
| – Big Bend substation ………………………………………………………………………… |  |  | 2016 | 15 |  | 41 | 56 | 56 | 0 |  | 0 | 0
| – Ruskin Dam safety and powerhouse upgrade ………………………………………………………………………… |  |  | 2017 | 235 |  | 513 | 748 | 748 | 0 |  | 0 | 0
| – John Hart replacement ………………………………………………………………………… |  |  | 2019 | 170 |  | 923 | 1093 | 1093 | 0 |  | 0 | 0
– Cheakamus units 1 and 2 generator
| replacement ………………………………………………………………………… |  |  | 2019 | 3 |  | 71 | 74 | 74 | 0 |  | 0 | 0
Columbia River power projects
| – Waneta Dam power expansion 3 ………………………………………………………………………………………. |  |  | 2015 | 297 |  | 53 | 350 | 350 | 0 |  | 0 | 0
|  | Total power generation and transmission …………………………………………………………………………………………………… |  |  | 3727 |  | 3214 | 6941 | 6514 | 0 |  | 130 | 297
Other
British Columbia Lottery Corporation
| – Gaming management system ........................................................................................ |  |  | 2015 | 79 |  | 20 | 99 | 99 | 0 |  | 0 | 0
Insurance Corporation of British Columbia
| – Business transformation program ........................................................................................ |  |  | 2016 | 193 |  | 71 | 264 | 264 | 0 |  | 0 | 0
|  | Total other ……………………………………………………………………………………………………………………………………….. |  |  | 272 |  | 91 | 363 | 363 | 0 |  | 0 | 0
|  |  | Total self-supported ............................................................................ |  | 7231 |  | 3392 | 10623 | 10196 | 0 |  | 130 | 297
|  |  | Total $50 million projects ............................................................................ |  | 10684 |  | 8183 | 18867 | 15434 | 1121 |  | 934 | 1378
1 | Only projects that receive provincial funding and have been approved by Treasury Board and/or Crown corporation boards are included in this table. Ministry service plans may include projects that still require final approval. Capital costs reflect current government accounting policy.
2 | Assets have been put into service and only trailing costs remain.
3 | Reflects the combined shares of Columbia Power Corporation (32.5 per cent) and Columbia Basin Trust (16.5 per cent) in their partnership with Fortis Inc. for the development of an electricity generating facility at the Waneta Dam south of Trail.
Note on O6: Peter Michielin: COA, ACA, other ministry, other source
Note on O66: Peter Michielin: COA, ACA, other ministry, other source